## Summary
Earned value: evm_example
Status period 2026-11. Costs in as entered.
What this means
- Each dollar spent so far has bought 90 cents' worth of the planned work: the work done has cost 11% over its budget.
- It is 2.2 reporting periods behind schedule, and at this pace finishes around period 35 of a 30-period plan.
- The most likely final cost is about 17,016; plan on 17,151 to be 80% sure. The budget of 15,500 has almost no chance (none of the simulations) of being enough.
- The contractor's estimate of 16,300 has less than a 1% chance of holding, so it is optimistic: it needs the rest of the program to go better than the record so far.
- There is 1 warning sign, on the Warning signs sheet; start with it.
- 2 accounts break the variance thresholds and owe a variance analysis report: '1.1 Air vehicle', '1.2 Software'.
Key numbers
Budget at completion (BAC) | 15500.4
Percent complete | 32.44%
CPI | 0.9024
SPI | 0.73044
SPI(t) | 0.84175
Schedule variance, periods (SV(t)) | -2.2155
Forecast final cost, P50 | 17015.6813
Forecast final cost, P80 | 17150.6595
Forecast finish period, P50 | 34.9873
Forecast finish period, P80 | 35.8591
Planned duration, periods | 30
Chance BAC is enough | 0%
Contractor EAC | 16300
Chance the contractor EAC holds | 0.155%
The Metrics sheet computes CV, SV, CPI, SPI, TCPI and the CPI-based EAC with Excel formulas from the BCWS, BCWP and ACWP beside them; click a cell to see how it was made.

## Metrics
BAC |  | 15500.4 |  | Blue columns are the data; the rest are Excel formulas on them and on BAC, except ES, which needs the baseline's shape and is a computed value.
Period | Time | BCWS (cum) | BCWP (cum) | ACWP (cum) | CV | SV | CPI | SPI | % complete | TCPI (to BAC) | IEAC (CPI) | ES | SPI(t) | Contractor EAC
2025-10 | 1 | 32.5 | 24.9 | 28 | [7 empty] | 0.76615 |  | 15500
2025-11 | 2 | 127 | 75.7 | 82.1 | [7 empty] | 1.4571 |  | 15561.5
2025-12 | 3 | 294.1 | 171.3 | 188.7 | [7 empty] | 2.2651 |  | 15623
2026-01 | 4 | 539.5 | 310.3 | 346 | [7 empty] | 3.066 |  | 15684.6
2026-02 | 5 | 866.1 | 498.4 | 558.7 | [7 empty] | 3.8325 |  | 15746.2
2026-03 | 6 | 1274 | 760.3 | 846 | [7 empty] | 4.6761 |  | 15807.6
2026-04 | 7 | 1761.4 | 1070 | 1198.1 | [7 empty] | 5.4999 |  | 15869.2
2026-05 | 8 | 2324.4 | 1424 | 1608.5 | [7 empty] | 6.3078 |  | 15930.8
2026-06 | 9 | 2957.5 | 1860.2 | 2097.2 | [7 empty] | 7.1755 |  | 15992.4
2026-07 | 10 | 3653.6 | 2390.2 | 2735.6 | [7 empty] | 8.1039 |  | 16053.8
2026-08 | 11 | 4404.3 | 2979.1 | 3380.3 | [7 empty] | 9.031 |  | 16115.4
2026-09 | 12 | 5200.2 | 3640 | 4115.4 | [7 empty] | 9.9805 |  | 16177
2026-10 | 13 | 6030.6 | 4357.8 | 4873.5 | [7 empty] | 10.9381 |  | 16238.5
2026-11 | 14 | 6884.5 | 5028.7 | 5572.6 | [7 empty] | 11.7845 |  | 16300

## Warning signs
flag | raised | detail
TCPI to the EAC exceeds the CPI by more than 0.10 |  | TCPI(EAC) 0.976 against CPI 0.902: to land on the EAC the remaining work has to run at a CPI of 0.976, against 0.902 so far.
Contractor EAC below every independent EAC | YES | EAC 16,300.0 against the lowest independent EAC 16,773.4.
EAC implies the CPI recovering by more than 0.10 after 20% complete |  | The EAC implies a final CPI of 0.951, against 0.902 at 32% complete; programs rarely recover 0.10 past 20%.
SPI has recovered but SPI(t) has not |  | SPI 0.730, SPI(t) 0.842 at 32% complete: late in a program SPI returns towards 1.0 whatever the schedule.
TCPI to BAC above 1.10 |  | Finishing within budget needs a CPI of 1.055 from here.
Earned value exceeds the budget at completion |  | Earned value is 32% of the budget of 15,500.4. Check the BCWP figures, and whether the budget at completion is right.

## Forecast
Simulated from the program's own record; see the Assumptions sheet.
confidence | eac | finish
10% | 16694.5632 | 33.4781
20% | 16825.205 | 33.913
30% | 16905.7715 | 34.3965
40% | 16968.9991 | 34.7343
50% | 17015.6813 | 34.9873
60% | 17058.248 | 35.2607
70% | 17101.2258 | 35.51
80% | 17150.6595 | 35.8591
90% | 17258.7876 | 36.395

## Accounts
Status period values per control account, worst CPI first.
account | BAC | BCWS | BCWP | ACWP | CV | SV | CPI | SPI | SPI(t) | IEAC (CPI)
1.2 Software | 4000.2 | 1776.7 | 1233.7 | 1395.5 | -161.8 | -543 | 0.88406 | 0.69438 | 0.81948 | 4524.827
1.1 Air vehicle | 9000.2 | 3997.4 | 2740.5 | 3030.2 | -289.7 | -1256.9 | 0.9044 | 0.68557 | 0.81403 | 9951.6169
1.3 Systems engineering | 2500 | 1110.4 | 1054.5 | 1146.9 | -92.4 | -55.9 | 0.91943 | 0.94966 | 0.971 | 2719.0612

## Data checks
Questions to ask about the data before trusting the metrics. A negative period value can be a legitimate correction.
account | period | check | detail

## Variance reports
Accounts whose cumulative variance breaks the thresholds ({'cv_pct': 10.0, 'sv_pct': 10.0, 'cv_dollars': None, 'sv_dollars': None}).
account | cv | cv_pct | sv | sv_pct | cpi | spi | why
1.1 Air vehicle | -289.7 | -10.5711 | -1256.9 | -31.4429 | 0.9044 | 0.68557 | cost variance -289.70 (-10.6%); schedule variance -1,256.90 (-31.4%)
1.2 Software | -161.8 | -13.115 | -543 | -30.5623 | 0.88406 | 0.69438 | cost variance -161.80 (-13.1%); schedule variance -543.00 (-30.6%)

## Assumptions
Setting | Value
status period | 2026-11
BAC | 15500.4
simulated completions | 20000
seed | 0
units | as entered
variance thresholds | {"cv_pct": 10.0, "sv_pct": 10.0, "cv_dollars": null, "sv_dollars": null}
Notes
Drawn from 14 periods of the program's own performance, with persistence 0.90 between periods.