## Elements
Element | Point Estimate | Low | Most Likely | High | Distribution
1.0 Program management | 12 | 11 | 12 | 18 | triangular
2.0 Systems engineering | 18.5 | 17 | 18.5 | 28 | triangular
3.0 Antenna subsystem | 42 | 37 | 42 | 72 | triangular
4.0 Software | 36 | 31 | 36 | 90 | triangular
5.0 Facilities | 22 | 20 | 22 | 31 | pert
6.0 Integration and test | 15 | 13 | 15 | 30 | triangular
7.0 Training and support | 6.5 | 6 | 6.5 | 10 | pert
8.0 Initial spares | 4

## Risks
Risk | Probability | Low | Most Likely | High | Element
Antenna vendor requalification | 25% | 4 | 6 | 10 | 3.0 Antenna subsystem
Cyber accreditation rework | 40% | 2 | 3 | 6 | 4.0 Software
Site permitting delay | 15% | 1.5 | 3 | 5 | 5.0 Facilities

## Correlation
Element A | Element B | Correlation
4.0 Software | 6.0 Integration and test | 0.6
1.0 Program management | 2.0 Systems engineering | 0.5
2.0 Systems engineering | 4.0 Software | 0.4

## Settings
Setting | Value
Units | millions
Default Correlation | 0.3
Iterations | 20000
Seed | 1

## Instructions
Sheet or topic | What to put there
What this is | A cost estimate with its uncertainty. ce-core cost-risk --data <this file> simulates it and says how much it takes to be 50%, 80% or 90% sure, which elements and risks drive that, and what the correlation between elements adds.
Elements sheet | One row per WBS element. Element is its name. Point Estimate is the number in the estimate. Low, Most Likely and High are the range you believe: Low the least it could plausibly cost, High the most. Leave Low and High blank for an element with no uncertainty (it is carried at its point estimate).
Distribution | Optional. triangular (the default) spreads the chance evenly along the three points; pert bunches it toward the most likely; uniform treats every value between Low and High alike and ignores the most likely.
Risks sheet | Things that may or may not happen. Probability is the chance it does (0.3 or 30%). Low, Most Likely and High are what it costs if it does. Element is optional and only labels the report. Delete the rows if there are no risks.
Correlation sheet | Pairs of elements that tend to overrun together, and how strongly (0 none, 1 in lockstep; 0.2 to 0.3 is typical, 0.5 or more for elements driven by the same thing). Every pair not listed takes the Default Correlation on the Settings sheet. Leaving correlation out makes the P80 too low.
Settings sheet | Units labels the money (thousands, millions or any word). Default Correlation applies to every pair not listed. Iterations and Seed control the simulation; the same seed gives the same answer.
Money | Use one unit and one dollar basis (for example constant FY2026 $M) throughout.